## Slide 1: SFAA Year 2 Action plan
Final Draft 2025

## Slide 2: Theme: Good Food Partnership
Objective | Action | Who/responsibility
Strengthen the existing partnership, identifying opportunities for collaboration and addressing gaps in the membership | Develop a SFAA workplan, focusing on collaboration and coordination between food support organisations. This workplan could also include how to include the "Resident Voice" within the partnership, as this is a gap in membership for the partnership. | SFAA SG, SFAA Coordinator/Admin
Develop guidance to help colleagues across the Council embed sustainable food in their work. | Develop a Council workplan that focuses on how sustainable food can be embedded across the council in different departments. | Public Health, SFAA Coordinator/Admin

## Slide 3: Theme: Good Food Partnership
Objective | Action | Who/responsibility
Strengthen the existing partnership, identifying opportunities for collaboration and addressing gaps in the membership | Establish working groups (as required) which consider key issues e.g. the future of Food Banks and propose future actions on these issues. | SFAA SG, SFAA Coordinator/Admin, Public Health
Build good governance processes so that Southwark Food Action Alliance is accountable, transparent, democratic and representative of local communities | Develop good governance for SFAA, including Terms of Reference for SFAA Steering Group. | SFAA SG, SFAA Coordinator/Admin

## Slide 4: Theme: Healthy People, Healthy Planet
Objective | Action | Who/responsibility
Promote a ‘no wrong door’ approach to those reporting food insecurity, signposting and referring appropriately to food help and other relevant support and advice. | A “Vision for food banks” working group is set up and working together collaboratively on a vision for food banks. This group also feeds into the council’s Right to Food group. This Working Group develops guidance on signposting and referring to income maximisation services is refreshed and training provided to frontline council staff and staff in VCS, NHS and other organisations. | SFAA, Vision for food banks WG

## Slide 5: Theme: Good Food Economy
Objective | Action | Who/responsibility
Support businesses and markets to facilitate shorter supply and distribution chains | Set up a working group to focus on creating stronger direct links to local food growers and farmers - e.g. explore Better Food Shed scheme (supplies local produce grown on organic farms to food shops, schools and education services, holiday activities and food programmes, social care services, community kitchens, NHS services). As part of this, define what "local" means when buying local food and businesses. | SFAA, Council: Public Health, Local Economy, Community Gardening, Planning

## Slide 6: Theme: Strong and Connected Communities
Objective | Action | Who/responsibility
Develop active and thriving food networks at the neighbourhood level connecting residents with local sustainable food activities | Residents make pledges to support Good Food Southwark and how they can support their neighbourhood on food. | Public Health & SFAA, discuss with Citizens UK, SGTO, TRAs and other resident groups
Develop a stronger culturally appropriate food offer for diverse communities | With the Culturally Appropriate working group, deliver a programme of work to support provision and access to culturally appropriate food: i) bulk purchasing coalition & small grants, ii) recipe book, iii) explore Rose Voucher extension | Public Health, SFAA

## Slide 7: Theme: Food Security and Right to Food
Objective | Action | Who/responsibility
Provide pathways to advice and practical help by having key professionals and volunteers trained in the Dignity Principles and Screening for risk of hunger and malnutrition | Deliver Dignity Training offer to Council and VCS and pilot with key businesses. | SFAA Dignity Champions
Campaign for national action to address the causes of poverty and mitigate the impact of the rising cost of living. | Encourage initiatives that advocate for improved welfare or food support for residents, in particular, auto-enrolment for Healthy Start and FSMs. Consider writing to National government. | SFAA, Council, Cabinet